## Blocked by Infra (26)
Tier-1 NL Scenarios Blocked by Infrastructure — 26 of 54 (per infra-requirements.md)
Scenario ID | Category | Scenario Name | Priority | Infra Blocker | Fault Required by Framework Spec | Why It Cannot Be Run To Spec Today
NL-D-02 | NL-D Durability | Durability under host power loss | P0 | Request 2 — Power control | Abrupt host power loss during active WAL flush under 1000 TPS; zero transactions acknowledged lost (RPO=0). | No API or mechanism to force power-off. SIGKILL leaves OS running to flush dirty buffers; §3 proves kill tests mask data loss that occurs under real power cuts.
NL-D-03 | NL-D Durability | Storage write-loss injection (dm-flakey) | P0 | Request 1 — Data disk | dm-flakey drops block writes for 5 s during commit; expect clean startup refusal or RPO=0 recovery. | dm-flakey must be inserted below PGDATA filesystem. Target has PGDATA on root LV with VFree=0; no DM shim can be inserted under live OS root.
NL-D-04 | NL-D Durability | Durability across synchronous_commit levels | P0 | Request 2 — Power control | Compare data loss across off, local, on under abrupt power cut; loss must strictly match theoretical bounds. | Requires abrupt power loss. Process termination does not discard unflushed kernel cache, masking difference between sync_commit levels.
NL-D-05 | NL-D Durability | Torn page / partial write | P0 | Request 2 — Power control | Induce 8 KB torn page via power severance mid-sector write; full_page_writes must restore torn block. | Torn pages are hardware/power phenomena. Process termination allows OS kernel to complete in-flight sector writes.
NL-D-06 | NL-D Durability | Volatile controller cache detection | P0 | Request 2 — Power control + Request 1 — Data disk | Detect battery-backed write cache failure by evaluating data loss on a cache=writeback volume after power cut. | Requires both a dedicated secondary volume configured with cache=writeback AND abrupt power control to discard cache.
NL-C-04 | NL-C Crash & Recovery | Recovery time versus WAL volume | P0 | Request 1 — Data disk | Generate 16 GB of WAL under sustained workload, terminate instance, and measure crash recovery RTO scaling. | Generating 16 GB of WAL on shared root filesystem risks filling the OS disk; pg_wal must reside on dedicated >=30 GB volume.
NL-W-01 | NL-W WAL & Archiving | Commit durability with markers | P0 | Request 2 — Power control | Write sync markers to WAL, cut power, and verify every marker acknowledged to client is recovered on startup. | Cannot test true WAL-to-media durability without power loss. Process kill leaves OS to flush buffers to disk.
NL-W-02 | NL-W WAL & Archiving | WAL segment boundary crash | P0 | Request 2 — Power control | Cut power precisely during WAL file switch and rename (at 16 MB boundary); verify recovery does not orphan segment. | Segment rotation involves rename() and fsync(). OS process termination finishes directory updates; only power loss tests corruption.
NL-W-04 | NL-W WAL & Archiving | Archive command failure | P1 | Request 1 — Data disk | Set archive_command to fail for 30 min; verify pg_wal stays <= 2x max_wal_size + backlog and does not exceed 90% fs capacity. | Requires isolated pg_wal and pgarchive filesystems. On shared root filesystem, accumulated WAL spills into OS disk.
NL-W-05 | NL-W WAL & Archiving | Archive under sustained pressure | P1 | Request 1 — Data disk | Throttle archive_command to 50% of WAL generation rate; verify database throttles WAL generation before disk full. | Requires separate pgwal and pgarchive mounts to evaluate backpressure boundaries without exhausting OS root filesystem.
NL-W-06 | NL-W WAL & Archiving | Archive gap mid-chain | P1 | Request 1 — Data disk | Simulate missing WAL segment in archive repository; verify PITR aborts at gap without data corruption. | Requires isolated pgrestore (60 GB) and pgarchive (30 GB) volumes to perform full basebackup restore and replay.
NL-W-07 | NL-W WAL & Archiving | pg_wal filesystem full | P0 | Request 1 — Data disk | Fill pg_wal filesystem to 100% under heavy commit load; verify PostgreSQL executes clean PANIC without corrupting state. | pg_wal shares root filesystem /. Filling pg_wal to 100% exhausts root disk and crashes the host OS rather than isolating DB PANIC.
NL-R-03 | NL-R Resource Exhaustion | Data filesystem full | P0 | Request 1 — Data disk | fallocate data filesystem to 100% under write load; verify transaction rollback with disk full error and clean recovery. | PGDATA shares root filesystem / on /dev/mapper/vg0-lv--0. Filling it fills /, taking down sshd, syslog, systemd, and the OS.
NL-R-08 | NL-R Resource Exhaustion | Temp space exhaustion | P2 | Request 1 — Data disk | Fill temp_tablespaces to 100% with large disk sort; verify other sessions maintain >=95% baseline throughput. | temp_tablespaces is unset today. Sort spills land in PGDATA which shares root filesystem /.
NL-N-01 | NL-N Noisy Neighbour | Hypervisor CPU steal | P0 | Request 5 — Co-tenant VM | Induce 40% hypervisor CPU steal (%st) via neighbouring VM on same CPU socket; verify attribution to steal, not DB load. | Requires a confirmed co-tenant VM on the same physical hypervisor socket. VMs on separate hosts share nothing.
NL-N-03 | NL-N Noisy Neighbour | Shared storage IOPS exhaustion | P0 | Request 5 — Co-tenant VM + Shared storage | Exhaust shared SAN/NAS IOPS pool from neighbour VM; verify database handles disk latency spikes without corruption. | Requires co-tenant VM AND confirmation that target storage volume is shared rather than dedicated local NVMe.
NL-N-04 | NL-N Noisy Neighbour | Host memory pressure / ballooning | P1 | Request 5 — Hypervisor ballooning control | Trigger hypervisor memory reclaim (ballooning) on target instance; verify PostgreSQL gracefully adapts buffer allocations. | Target VM has fixed 16 GB memory. Dynamic ballooning requires hypervisor API access to inflate balloon driver.
NL-N-05 | NL-N Noisy Neighbour | Network bandwidth contention | P1 | Request 5 — Co-tenant VM + Request 6 — Standby node | Flood hypervisor virtual NIC with neighbour traffic; measure impact on streaming replication lag. | Requires co-tenant VM for network flood AND a standby replica node to measure streaming replication lag.
NL-N-08 | NL-N Noisy Neighbour | Sustained grey degradation (4 h) | P0 | Request 5 — Co-tenant VM | Subject target to intermittent low-level neighbor resource stealing over 4 hours; verify monitoring detects degradation. | Requires persistent co-tenant VM on the same host generating realistic non-deterministic interference.